## Sheet1
TASK # | Product | Due Date | Date | Revised Due Date | Date Approved | Notes
|  | in SCR | Delivered | For Report
1 | Source Area Investigation Workplan | 2003-04-25 | 2003-04-25 |  | 27-May-03 w/conditions
2 | Community Relations Plan | 2003-05-14 | 2003-05-14 | 2003-10-01
3 | Risk Assessment Workplan | 2003-05-14 | 2003-05-14 |  | 2003-09-09 | Requested that Final Risk Assessment be Due on 5-Feb-04 And include Indoor-Air from Homes
4 | Area Well Survey | 2003-05-28 | 2003-05-28 | 2003-10-14 |  | Access to Private wells in Progress. Data from well sampling will be included in Final Risk Assessment
5 | Remedial Investigation Workplan | 2003-06-27 | 2003-08-15 |  | 2003-10-28 | Approved plan
6 | Source Area Investigation Completion Report/IRM Workplan | 2003-08-15 | 2003-11-15 |  | 2003-11-17 | Source Area Investigation Satisfactory, Interim Measure recommendation to wait for final remediation of Task 9 is acceptable.
7 | Implementation of Source Area Interim Measure |  |  |  |  | Groundwater concentrations do not indicate that interim remedy is needed at this time.
8 | New (Final) Risk Assessment | 2004-02-05
9 | Remedial Investigation Workplan | 2004-03-19
10 | Feasibility Study & Cleanup Standards | 2004-08-13