## Sheet1
Description of Action and Objectives | Category | Steps1 | Reporting Requirements and Desired Outcome2 | Comments/References | First Permit Term
1. Pollution Prevention / Source Control
1.1 Removal of PCBs and PCB-containing equipment:
1.1.1 Evaluate existing PCBs and PCB-equipment removal programs. The goal is to determine whether municipalities should supplement existing programs. | 4 | 1. Research and evaluate current regulations and programs (e.g., DTSC, TSCA, RCRA) and level of implementation. | Report that evaluates current regulations/programs and levels of implementation, identifies any shortfalls, and provides recommendations for next steps (complete by end of Year 1). | Decision Point: are current activities sufficient or should municipalities consider incorporating PCBs and PCB-equipment identification/removal into stormwater program facility inspections? If the latter proceed to 1.1.2. | BASMAA Joint Program
1.1.2 Incorporate PCBs and PCBs-equipment identification/removal into existing stormwater program facility inspections. The goal is to remove PCBs or remove PCB-equipment and properly dispose/recycle. | 3 | 1. Compile and adapt existing information on types of equipment and facilities that may contain PCBs. Evaluate whether most or all such facilities are included in existing stormwater program inspections. | Develop outreach materials, training materials and inspection checklist. | Ettie St. study is one source of information. | BASMAA Joint Program
|  | 2. Pilot scale training of facility inspectors to identify potential PCBs and PCB-equipment. |  | Inspectors should also be trained to enforce good spill prevention and response practices. | One Case Study per Countywide program
|  | 3. Implement pilot PCBs and PCB-equipment identification/removal programs. | Report results of pilot program effectiveness (complete by end of Year 4). | May include developing regulatory incentives to replace equipment. Decision Point: are pilot programs effective enough to merit expanding to case studies or full implementation? <We still need to define "effective."> | One Case Study per Countywide program
1.2 Management of construction activities:
1.2.1 Evaluate managing PCB-containing materials and wastes during construction, including building demolition/remodeling and improvement (e.g., window replacement) activities. The goal is to determine whether municipalities should implement this type of program. | 3 | 1. Evaluate potential presence of POCs (including PCBs) at construction sites, current material handling and disposal regulations/programs (e.g., municipal ordinances, RCRA, TSCA) and current level of implementation. | Report that evaluates current regulations and level of implementation and identifies shortfalls (complete by end of Year 1). | Include other POCs in this program. Include researching lessons learned from asbestos abatement programs and possible future tie-in. | BASMAA Joint Program
|  | 2. Develop sampling and analysis plan (includes research on when, where and which construction materials potentially contained PCBs). | Prepare sampling and analysis plan (complete by end of Year 1). |  | BASMAA Joint Program
|  | 3. Implement sampling and analysis program. | Prepare report with results and recommendations for next steps (complete by end of Year 2). | Decision Point: do the results of the sampling and analysis indicate the need to develop a pilot program to manage PCB material and wastes during building demolition and improvement? | BASMAA Joint Program
|  | 4. Develop/select proposed BMPs to reduce or prevent discharges of PCBs during building demolition/remodeling. The BMPs will focus on methods to identify, handle, contain, transport and properly dispose of PCB-containing building materials. | Prepare report with BMPs (complete by end of Year 3). |  | BASMAA Joint Program
|  | 5. Develop a model implementation program and pilot test BMPs, including developing model municipal regulatory controls/policies and a program to train and deploy inspectors. | Report results of pilot program effectiveness (complete by end of Year 4 or 5). |  | One Case Study per Countywide program
1.2.2 Evaluate construction site erosion control. The goal is to ensure that current construction site stormwater pollution programs minimize or prevent discharges of sediment and potentially associated particle-bound POCs. This is unlikely to be a big deal for PCBs at most construction sites. This might be an issue since this is the only action on this list in category 1 that is an actual action. All other Category 1 items are paper exercise. | 4 | 1. Evaluate existing construction site erosion control programs are fully implemented. | Report evaluating program effectiveness and recommending improvements, if needed (complete by end of Year 1). | Decision Point: based on the level of success of program, maintain at current level, expand, scale back or discontinue. | Full implementation
2. Investigation and Abatement of Areas with Elevated PCBs in Soils/Sediments
2.1 Drainage-focused Activities
2.1.1 Investigate and abate on-land drainages with elevated PCBs in soils and/or sediments. The goal is to identify and abate PCB source areas, including private properties, public right-of-ways and stormwater conveyances with accumulated sediments. This section should be numbered in a consistent manner with the other sections. | 2 | 1. Interview municipal staff and review municipal databases, other agency files, and other available information to identify potential PCB source areas and areas where sediment accumulates, including within stormwater conveyances. | Needs an interim Completion Date Commitment | This control measure addresses drainages known to have elevated PCBs, but does not include identifying additional drainages. The Ettie Street Proposition 13-funded study will help pilot test this control measure. | Full implementation
|  | 2. Conduct driving/walking surveys of the drainage to further identify potential source properties, using a checklist of attributes associated with past or current use of PCBs. Examine sediment accumulation areas and evaluate mobilitization potential. | Report on suspect properties and sediment accumulation areas (complete by end of Year 1). Needs an interim Completion Date Commitment | The Ettie Street Study inspection checklist should be reviewed and refined as needed. | Full implementation
|  | 3. Test sediments and soils from suspect properties and/or conveyances for PCBs to help identify where abatement efforts should be focused. | Report on sampling and analysis results (complete by end of Year 2). Needs an interim Completion Date Commitment | When prioritizing which areas to sample, consider PCB concentration, mass of sediment and mobilization potential. Decision Point: do results of sampling and analysis indicate that an abatement program is needed? | Full implementation
|  | 4. Identify/evaluate funding and/or responsible parties to perform abatement, abatement options, and which agencies and regulatory programs should provide oversight for abatement activities (e.g., USEPA, CERCLA, DTSC, State CAA, municipal ordinances). Municipalities also have responsibilities for remedial actions in certain cases. This table needs to clearly state this as there will be cases with no RP and a fast response may be needed Identify areas for expedited abatement based upon exceedence of a threshold of loading potential (to be determined based upon including factors such as PCB concentration, mass of sediment and mobilization potential) and/or human health There already are thresholds such as CHSSLs. | Report on proposed remedial activities, funding, agency oversight and schedule (complete by end of Year 3). Needs an interim Completion Date Commitment | Clean Estuary Partnership Project 4.28 report provides some guidance. Include evaluation of optimal control strategy (e.g., abate upstream source areas before downstream sediment accumulation areas). | Full implementation
|  | 5. Conduct abatement program.3 | Report results of pilot program effectiveness (complete by end of Year 4). | Decision Point: based on the level of success of the case studies, maintain, expand, or scale back the number of case studies or discontinue. | Full implementation
3. Soil / Sediment Control
3.1 Routine sediment management practices:
3.1.1 Using existing information evaluate the frequency of routine sediment management practices including street sweeping and maintenance of stormwater conveyance facilities (e.g., storm drain inlets, pump stations, channels, detention facilities). The goal is to evaluate the cost-effectiveness relative to reducing pollutant loads of increasing current typical frequencies. | 4 | 1. Complete ongoing desktop studies using existing information to evaluate the cost-effectiveness relative to reducing pollutant loads of increasing current typical frequencies. | Report that evaluates maintenance practice frequency based on existing data and provides recommendations for next steps, if needed (complete by end of Year 1). | Decision Point: is additional evaluation of maintenance practice frequency needed? | BASMAA Joint Program
3.1.2 Evaluate existing information on high-efficiency street sweepers. The goal is to evaluate the cost-effectiveness of high-efficiency street sweeping relative to reducing pollutant loads. | 4 | 1. Compile and evaluate existing information on street sweeper efficiency . | Report evaluating existing information on the cost-effectiveness of using high-efficiency street sweepers and, if needed, providing recommendations for follow-up studies (complete by end of Year 1, if data needed are available). | Decision Point: are follow-up studies on high-efficiency street sweepers needed? | BASMAA Joint Program
Add another row as a placeholder to implement 3.1.1 and 3.1.2 if deemed worthwhile.
4. Stormwater Treatment
4.1 Stormwater runoff treatment retrofits for fine sediment control:
4.1.1 Evaluate existing information on stormwater treatment retrofits in context of all BMPs for PCBs and other particle-bound pollutants. The goal is to determine whether stormwater treatment retrofits are a potentially cost-effective method to address PCBs and other particle-bound pollutants, and if so, to compile information to inform pilot-testing design. | 4 | 1. Research and evaluate existing information on stormwater treatment retrofits in context of all BMPs for PCBs and other particle-bound pollutants. | Report that evaluates existing information on stormwater treatment retrofits in context of all BMPs for PCBs and other particle-bound pollutants and, if needed, compiles information to inform pilot-testing design (complete by end of Year 1). | Note overlap with SFEI Proposition 13-funded project. Decision Point: are stormwater treatment retrofits a potentially cost-effective method to address PCBs and other particle-bound pollutants? If yes, proceed to 4.1.2. | BASMAA Joint Program
4.1.2 Install treatment systems. The goal is to use stormwater treatment retrofits to remove PCBs from stormwater discharges. | 3 | 1. Identify locations that present opportunities to install treatment systems (i.e., detention basins, sand filters, infiltration basins, wetlands) and assess the best treatment option for those locations. This assessment should identify potential sites draining a variety of landuse types throughout all program areas and discuss feasibility/economonic issues. | Report on candidate sites and proposed treatment type for those sites. Report should include assessment of at least 15 sites spanning all program areas and provide recommendation for five sites for pilot studies (complete by end of Year 2) | All programs should share this task. Location choice may be informed by drainage-focused investigations (see Section 2). | One Case Study per Countywide program
|  | 2. Perform pilot studies. Pilots should span treatment types and drainage characteristics (e.g., particle size distribution). | Report results of pilot program effectiveness (complete by end of Year 4). |  | One Case Study per Countywide program
3. Add row to Implement on a large scale if appropriate.
4.2 Stormwater treatment by POTWs:
4.2.1 Evaluate existing information on stormwater treatment by POTWs. The goal is to determine whether this option is a potentially cost-effective method to address PCBs and other particle-bound pollutants, and if so, to compile information to inform pilot-testing design. | 4 | 1. Research and evaluate existing information on stormwater treatment by POTWs. | Report that evaluates existing information on stormwater treatment by POTWs and, if needed, compiles information to inform pilot-testing design (complete by end of Year 1). | Review should include EBMUD and Sunnyvale projects. Decision Point: is stormwater treatment by POTWs a potentially cost-effective method to address PCBs and other particle-bound pollutants? If yes, proceed to 4.2.2. | BASMAA Joint Program
4.2.1 Route stormwater discharges to POTW. The goal is to use POTWs to remove PCBs and other pollutants from stormwater discharges. | 3 | 1. Prepare list of existing pump stations in the region urbanized areas, and evaluate what they drainage area for the presence of PCBs and evaluate the feasibility of routing to POTWs. The purpose is to identify candidate opportunities. Also Work with BACWA to work out program structure, including cost sharing agreements. | Submit report on the list of pump stations, their drainages and feasibility considerations with routing to POTW for each pump station (complete by end of Year 2).Year 1 | All programs should share this task. Location choice may be informed by drainage-focused investigations (see Section 2). Requirements need to be incorporated in POTW NPDES permits and PCB TMDL needs to provide impetus for implementation. | BASMAA Joint Program
|  | 2. Implement pilot studies in 3 to 4 locations to represent a range of conditions and land uses. | Report results of pilot program effectiveness (complete by end of Year 4). |  | One Case Study per Countywide program
3. Add row to Implement on a large scale if appropriate.
5. Other Activities
5.1 Development of a risk reduction program
5.2 Fate and transport studies | 1 | By particpating in RMP or equivalent, conduct or cause to be conducted studies aimed at better understanding PCBs fate, transport, and biological uptake in San Francisco Bay and tidal areas. | Reporting by RMP or equivalent program (as completed). |  | BASMAA Joint Program
5.3 Consult with Caltrans regarding Caltrans portion of allocation | 1 | Develop an equitable allocation-sharing scheme in consultation with Caltrans to address Caltrans roadway and non-roadway facilities in the program area. | Report the details to the Water Board (complete by end of Year 1). |  | BASMAA Joint Program
6. Monitoring Activities
6.1 Estimating stormwater loads or loads avoided | 1 | Develop a monitoring system to quantify either PCBs loads or loads reduced through treatment, source control, and other management efforts. Perform in conjunction with Task #2.. | PCB monitoring system plan (complete by end of Year 1). |  | Joint Program
|  | Demonstrate progress toward (a) the interim loading milestone, or (b) attainment of the program area allocations, by using one of the following methods: 1) Quantify the annual average PCBs load reduced by implementing control measures; 2) Quantify the PCBs load as a rolling five-year annual average using data on flow and water column PCBs concentrations; or, 3) Quantitatively demonstrate that the PCBs concentration of suspended sediment that best represents sediment discharged with urban runoff is below the suspended sediment target. This language does not work well for PCBs: e.g. no sediment target and expensive water column analytical method. I'll work on this. | PCB monitoring system report (complete by end of Year 4). |  | Joint Program
Notes:
1 - Steps are in chronological order and should be completed within the first four years of the five-year permit term, unless a step is cancelled following a decision point.
2 - The schedule is based on evaluating each BMP on a technical and standalone basis.
3 - Potential abatement options include the following:
Soil/sediment removal and treatment or proper disposal.
Capping to prevent pollutant mobilization.
Paved surface cleaning (e.g., high-efficiency street sweeping or power washing with capture and proper disposal of rinsate).
Stormwater treatment.
Removal of sediments at point of discharge and treatment or proper disposal.